## Sheet1
Item/Function | Potential Failure Mode | Potential Effects of Failure | SEV | CLASS | Potential Cause/ Mechanism of failure | OCCUR | Current design control prevention | Current design control detection | DETECT | RPN | Recommended Actions | Responsibility & Target completion date | Action Results
[13 empty] | Actions taken | SEV | OCC | DET | RPN
Driveshaft | Splines worn out | No power transmitted to wheel | 8 | C | Shock and fatigue loading | 6 | Torque calculations, conservative design methodology (FOS) | Visual check for excessive noise | 7 | 336 |  | Powertrain |  |  |  |  | 336
| Shaft breakage due to | Excessive vibrations | [5 empty] | very slow pickup |  |  |  | Aug 15,2013
torsion/shear
Engine | Mechanical | Explosion, Permanent damage to engine | 10 | C | Lack of clean air and fuel to maintain | 1 | Proper space to ensure cooling of the engine |  | 10 | 100 | Regular maintainance | Powertrain |  |  |  |  | 100
[5 empty] | operation. |  | Check oil level daily, first 5 hours then after every 25 hours of working |  |  |  | Handled with precaution
[5 empty] | Using choke most of the times - keeping |  | Proper engine mounting
[5 empty] | fuel valve on |  | Not run engine with choke ON
Improper lubrication
Gearbox | Tooth breakage | No power transmission | 8 | C | Shock and fatigue loading | 4 | Max speed of 60kmph | Visual check for oil level | 8 | 256 | Oil level indicator in dashboard | Powertrain & Electrical | Prelimiary review on sensors | 8 | 4 | 5 | 160
| Overheating | Vibrations |  |  | Excessive stress developed |  | Proper lubrication as required | [5 empty] | in gearbox
[5 empty] | Improper lubrication |  | Bending moment calculations
CVT | Belt breakage | No/ Reduced power transmission | 8 | C | Improper belt tension | 4 | Proper CVT Tuning | Visual check for excessive noise of | 6 | 192 | Belt slip detector | Powertrain | CVT Test Rig | 8 | 4 | 3 | 96
| Excessive slipping |  |  |  | Excessive heating |  | Air Cooling system for CVT | belt |  |  | Temperature monitor during test | Aug 20, 2013 | Design
[5 empty] | Shock loads | [5 empty] | CVT cover designed as per results
[5 empty] | Creep failure | [5 empty] | CVT Test Rig to be fabricated
CV Joint |  |  | 7 | S |  | 5 | Torque calculations | Visual check | 7 | 245 | Regular maintainence | Powertrain
1 | Grease dripping on ground |  | 7 |  | Torn CV Joit boots | 5
sprayed on chassis parts
Contamination by foreign particles
2 | Clicking or snapping noise | Reduced power transmission | 7 |  | Bent axle shaft | 5
when turning corners
Requirements | Smooth Power transmission | Engine failure | engine not start
Functions | Uniteruppted | CVT | CVT flung out |  | Belt break, excessive slip, heating
| All Terrain | Gearbox | gear teeth |  | lubrication,excessive torque
| Shock loads | Driveshaft, splines | worn splines
| Acceleration | Hub | aluminium |  | shear
|  | CV Joint | boot leak
|  |  | CV Joint corroded |  | foreign particle